# Glass⏧Grasie® — Plan van Aanpak

12-18 Month Roadmap | Qredits Financed12-18 Month Roadmap | Qredits Financed

## FASE 1: Setup & Foundation (Week 1–4)

Objective: Secure legal, financial, and operational foundation. Begin material sourcing.Objective: Secure legal, financial, and operational foundation. Begin material sourcing.

| Deliverable | Timeline | KPI / Gate |
| --- | --- | --- |
| KvK registration | Week 1 | Legal entity active |
| Van Dijken material contract signed | Week 2 | Supply locked in |
| WBSO filing | Week 2 | €23.975 tax credit eligible |
| Design tooling finalized | Week 3 | Production-ready files |
| First 10 jewelry pieces | Week 3 | Photo-ready, 10+ units |

## FASE 2: B2C Launch (Week 4–8)

Objective: Go live B2C channels, achieve first sales, establish proof of concept.Objective: Go live B2C channels, achieve first sales, establish proof of concept.

| Deliverable | Timeline | Target |
| --- | --- | --- |
| Website + Shopify live | Week 4–5 | Store operational |
| Instagram + TikTok content calendar | Week 4–5 | 2+ posts/week, organic reach |
| First online sales (jewelry) | Week 7 | €2.000–3.000 Q3 revenue |
| Woonaccessoires launch prep | Week 6–8 | 20 designs, 5 prototypes |

## FASE 3: B2B Entry (Week 8–12)

Objective: Open B2B channel (architects, interior designers); introduce architectural products.Objective: Open B2B channel (architects, interior designers); introduce architectural products.

| Deliverable | Timeline | Target |
| --- | --- | --- |
| B2B outreach list (architects/designers) | Week 8 | 150+ qualified contacts |
| B2B portfolio + pitch deck | Week 8–9 | 3 use-case mockups |
| First B2B conversations | Week 8–10 | 10+ discovery calls |
| WAZER delivery + setup | Week 11–12 | Machine operational |

## FASE 4: Scale & Optimization (Month 4–6)

Objective: Hit €5K–€6K/month burn; confirm break-even trajectory. Expand all product tiers.Objective: Hit €5K–€6K/month burn; confirm break-even trajectory. Expand all product tiers.

| Deliverable | Timeline | Target |
| --- | --- | --- |
| B2C revenue (Q4: jewelry + accessories) | Month 4–6 | €4.500–6.000/month |
| First B2B project (quote or LOI) | Month 5–6 | €1.000–2.000 order |
| Kunstobjecten launch (limited edition series) | Month 5–6 | 3–5 art pieces |
| Confirm operational break-even | Month 6 | €3K–€4K monthly burn |

## Financing Breakdown (Qredits €9.200 Loan)

| Use of Funds | Amount |
| --- | --- |
| WAZER Desktop machine | €7.500 |
| Installation + water/abrasive system setup | €1.200 |
| Initial abrasive + operational reserve | €500 |
| Total | €9.200 |

## Success KPIs & Milestones

| KPI | Timeline | Success Criteria |
| --- | --- | --- |
| B2C unit sales (jewelry) | Month 2 | 20+ units/month |
| B2B qualified leads | Month 3 | 3+ active conversations |
| Monthly revenue | Month 6 | €5.000–€6.000 (on track for €52.5K Y1) |
| Website conversion rate | Ongoing | 2–4% (jewelry); 1–2% (accessories) |
| Customer acquisition cost (CAC) | Month 4 | €15–€25/order (organic + paid) |
| Repeat purchase rate | Month 6 | 15%+ (jewelry); 8%+ (accessories) |

## FASE 5–6: Growth & Profitability (Month 7–18)

Year 1 target: €32.5K–€52.5K
Year 2 target: €89K–€133K
Focus: Expand B2B partnerships (architectural projects), grow B2C through retail partnerships (Design museums, Dutch design galleries), and optimize unit economics. WAZER depreciation write-off begins reducing tax burden.

## Risk Mitigation & Contingencies

• Supply risk: Signed material contract with Van Dijken ensures consistent access; secondary glass sources identified

• Equipment risk: WAZER has proven track record in maker/design studios; maintenance contract included

• Market risk: MAGNA and Vetrazzo prove market appetite; early traction from Art Rotterdam/DDW networks

• Founder dependency: Scalable team model in place; hired commercial associate by month 6 for operations + fulfillment

## Reporting & Governance

• Monthly: Revenue, CAC, repeat purchase rate, inventory levels, B2B pipeline

• Quarterly: Full P&L, KPI dashboard, milestone achievement, strategic adjustments

• Qredits reporting: Aligned with loan terms; transparency on unit economics, cash runway, and milestones achieved

Glass⏧Grasie® | Plan van Aanpak | April 2026Glass⏧Grasie® | Plan van Aanpak | April 2026